## Prosjektplanlegging
Project Planning
Gantt Chart for to-do activities | [6 empty] | Planned duration | [6 empty] | Planned start |  |  |  |  | % completed |  |  |  |  | Actual (after) | [7 empty] | % completed (after)
ACTIVITY | PLANNED START | PLANNED DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETED % | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Write down everything that's required | 1 | 1 | 1 | 4 | 80%
Creating a Gantt Chart | 1 | 1 | 1 | 1 | 100%
Write a proposal/planning document | 2 | 1 | 3 | 1 | 60%
Design the website for mobile | 2 | 1 | 1 | 1 | 40%
Design the website for media queries | 3 | 1 | 3 | 1 | 40%
Ask people about what they think about the design | 4 | 2 | 4 | 1 | 0%
Code the header of the home site (mobile) | 4 | 1 | 4 | 1 | 100%
Code the rest of the home site (mobile) | 5 | 2 | 5 | 2 | 100%
Code the Contact site (mobile) | 7 | 2 | 5 (desktop) | 1 | 100%
Code the Content site (mobile) | 8 | 2 | 5 (desktop) | 1 | 100%
Code the Exhibiton site (mobile) | 9 | 2 | 6 (desktop) | 1 | 100%
Code the Learn site (mobile) | 10 | 2 | 5 (desktop) | 1 | 100%
Code the smartpad view | 11 | 2 | 9 | 1 | 100%
Code the laptop view | 9 | 2 | 9 | 1 | 100%
Code the desktop view | 9 | 2 | 9 | 1 | 100%
Test the website on all platforms | 9 | 4 | 8 | 1 | 50%